## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Had some php and database issues due to testing. This issue was resolved on 4/3. The project is on schedule as stated on the Revised Project Timeline. Coding is moving forward and testing is beginning. | 
Status as of | 3-April-2019
Business Lead | Jim Worth
Project Manager | Shay Walker
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/20 | 
Design |  | 100% | 2/20 | 
Coding |  | 75% | 3/39 | 4/24
Testing |  | 25% | 4/17 | 4/24
Training Plan Development |  | 0% | 3/27 | 4/17
Deployment |  | 0% | 5/1 | 5/1
Go Live |  | 0% | 5/1 | 5/8
Hyper Care |  | 0% | 5/8 | 5/8
# | Key Accomplishments (Current Period)
1 | Php functionality is moving forward
2 | Login/Register Functionality is complete
3 | Testing Plan Developed
4 | News Page Functionality is complete
# | Upcoming Activities (Next Period through (04/10/2019)
1 | Continue constructing the Database
2 | User’s Manual Creation and Development
3 | Connection of Pages Finalized to Begin Testing
4 | Profile and Edit Profile Pages PHP Functionality
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Between building and testing some php and database connections were not functional. Database needed to be redone. | Low | Low | Consulted a professional in the area to resolve the functionality issues with the php and database. | Shay Walker | Low | 4/3
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
N/A |  |  |  |  |  |  | 
CairnConnect