## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Project is ahead of coding schedule. Code Freeze was established and worked well. Simple changes may need to be made to user interface on some pages. | 
Status as of | 17-April-2019
Business Lead | Jim Worth
Project Manager | Shay Walker
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/20 | 
Design |  | 100% | 2/20 | 
Coding |  | 97% | 3/29 | 4/24
Testing |  | 45% | 4/17 | 4/24
Training Plan Development |  | 100% | 3/27 | 4/17
Documentation |  | 15% | 5/1 | 5/1
Deployment |  | 0% | 5/1 | 5/1
Go Live |  | 0% | 5/1 | 5/8
Hyper Care |  | 0% | 5/8 | 5/8
# | Key Accomplishments (Current Period)
1 | Code & Functionality are primarily completed ahead of schedule
2 | Training Plan Development complete
3 | Implementation Plan Development complete
4 | Database Complete
5 | Search Results and Help desk pages are functional
# | Upcoming Activities (Next Period through (04/24/2019)
1 | SIT Testing
2 | UAT Testing
3 | Documentation/Bug Fixes
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
N/A |  |  |  |  |  |  | 
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
N/A |  |  |  |  |  |  | 
CairnConnect