## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Up to schedule (revised plan) Testing is proceeding Functionality is well underway Database construction is going well | 
Status as of | 27-March-2019
Business Lead | Jim Worth
Project Manager | Shay Walker
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/20 | 
Design |  | 100% | 2/20 | 
Coding |  | 50% | 3/39 | 4/24
Testing |  | 0% | 4/17 | 4/24
Training Plan Development |  | 0% | 3/27 | 4/17
Deployment |  | 0% | 5/1 | 5/1
Go Live |  | 0% | 5/1 | 5/8
Hyper Care |  | 0% | 5/8 | 5/8
# | Key Accomplishments (Current Period)
1 | Php functionality is moving forward
2 | Functionality is making large improvements and should be able to be ready on-time
3 | Testing as begun with preliminary and security
4 | Login Functionality is complete with Database
# | Upcoming Activities (Next Period through (04/03/2019)
1 | Continue constructing the Database
2 | Population of the Database (examples only for testing functionality)
3 | PHP functionality for registration will be finished
4 | PHP functionality for populating Pages with info from the Database
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
N/A |  |  |  |  |  |  | 
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
N/A |  |  |  |  |  |  | 
CairnConnect