## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Go Live went well Deployment Successful | 
Status as of | 1-May-2019
Business Lead | Jim Worth
Project Manager | Shay Walker
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/20 | 
Design |  | 100% | 2/20 | 
Coding |  | 100% | 3/29 | 4/24
Testing |  | 100% | 4/17 | 5/1
Training Plan Development |  | 100% | 3/27 | 4/17
Deployment |  | 100% | 5/1 | 5/1
Go Live |  | 100% | 5/1 | 5/8
Hyper Care |  | 100% | 5/8 | 5/8
# | Key Accomplishments (Current Period)
1 | Documentation and Edits Complete
2 | Successful Go Live
3 | Roadmap Presentation Complete
# | Upcoming Activities (Next Period through (05/8/2019)
1 | Continued Hypercare
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
N/A |  |  |  |  |  |  | 
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
N/A |  |  |  |  |  |  | 
CairnConnect