## Sheet1
Product Backlog for Olympus (Velocity = 25)
ID | As a…. | I want to be able to… | So that… | Story Points | Priority | Status | Sprint
17 | Young Adult/Teenager | Have access to at least 5 differing game styles within the laser tag arena | I can play multiple kinds of games/rounds and without getting bored | 13 | H | In progress | 1
18 | Caregiver a mentally handicaped child | Have access to a quiet/private sitting area with chairs, couches, and tables | If my child needs a break from the busyness and noise we can have a place to go without leaving | 8 | L | In progress | 1
3 | Grandparent | Have access to a parks spot that is 100 ft or less from an entrance | My grandshildren and I can get into the center without having to cross traffic | 3 | M | In progress | 1
1 | Shopper | have parking spaces available close to the entrances of the shopping center | I only have to walk at most 500ft to get to and form my car with my purchased items | 5 | L | Not Started | 2
2 | New Parent | Have a designated parking spot that has 3ft of extra room | I can get my stroller and child out of the car safely | 3 | M | Not Started | 2
13 | Store Owner/Renter | To have the availability to rent a 30, 100, or 500 sq. Ft. spaces | I can have the best space suited to my retail needs | 55 | H | Not Started | 2
4 | Physically Handicapped Community Member | Enter at any door and have access to automactic doors | I can easily and without assistance get into the center | 21 | M | Not Started | 2
28 | Physically Handicaped Community Member | Have access to at least 8 elevators throughout the center | I can from floor to floor with 3 minutes | 55 | M | Not Started | 2
33 | Grandparent | see signs for handicap spaces as soon as I enter the parking lot or from 300 ft away | I can easily and quick find a place to park | 13 | H | Not Started | 2
16 | Young Adult/Teenager | Have an observation deck with live feed cameras and monitors | I can watch my friends while they are still playing laser tag in the arena | 21 | H | Not Started | 2
24 | Teenager | Play a game of laser tag for less than $10 | I can afford to come and play laser tag | 2 | H | Not Started | 2
5 | Caregiver/Provider of Individuals with Special Needs | Have access to parks spaces less than 200ft away from an entrance with 3ft of extra space | I can easily get my clients out of our car and into the center safely. | 3 | M | Not Started | 2
31 | Shop Owner | have access to a storeroom that is at least 10ft by 30ft | I can have extra inventory on hand close by | 34 | H | Not Started | 3
37 | Parent | have 3 labeled hand sanitizer stations at each playground | my children and I can use handsanitizer before and after playing on the playgrounds | 13 | H | Not Started | 3
20 | Shopper | To have access to sushi and pizza in the food court | I can purchase food that I like while I am at the Shopping Center | 34 | H | Not Started | 4
21 | Shopper | To purchase coffee drinks and bakery item | I can enjoy coffee and pastries while I shop | 13 | H | Not Started | 4
12 | New Parent | Have a family restroom that has baby changing station in it | I can change my baby in a private environment as to not bother others. | 21 | L | Not Started | 4
19 | Parent | Have access to affordable child friendly restaurants that have a children's menu | I can purchase meals for my child at an affordable price | 21 | M | Not Started | 4
9 | Physically Handicaped Child | Have access to handicap/disability friendly swings | I can actually play on the playgrounds safely | 34 | H | Not Started | 5
26 | Parent | Take my child to a restroom with large 4ft-6ft wide stalls | I can assist my child in the restroom without the stall being to cramped | 13 | L | Not Started | 5
11 | Grandparent | have centrally located restrooms that are less than 100ft away from a restaurant and/or playground | I can easily and quickly find a restroom when I am with my family | 55 | M | Not Started | 5
39 | Teenager | Play in weekly laser tag tournaments that cost less than $20 to enter | I can impress and improve my laser tag skills with my friends | 21 | M | Not Started | 5
27 | Parent | Have access to at least one organic and whole foods market | I can do my grocery shopping while my teen is playing laser tag | 55 | H | Not Started | 5
10 | Parent | Sign my child/children in and out of child care within 3 minutes | I can quickly get to shop at a peaceful pace | 21 | H | Not Started | 6
29 | Teacher of physically handicaped children | Have access to tours with elevators, wide pathways, and wheelchair friendly activities | My students in wheelchairs can participate in the tours of the green houses and green energy facilities. | 13 | H | Not Started | 6
22 | Environmentalist | Shop at a center that only uses alternatives to plastic bags, straws, and paper towels | I can shop and visit a place where everyone is being environmentally conscious | 8 | H | Not Started | 7
23 | Elementary Teacher | To purchase tours that are less than $10 per student | All of my students can afford to come and learn about sustainable energy and urban farming | 2 | H | Not Started | 7
6 | Shopper | Have the map/directory of Titans Tower(Shopping Center) accessible outside of every 4th store | I don’t have to walk far or search for a directory of Titians Tower | 13 | L | Not Started | 7
14 | Elderly Community Member | Have access to at least 3 help/service desks | I can be able to ask for help and be served quickly. | 13 | L | Not Started | 8
15 | Elementary School Teacher | Have access to large group tours of the green house and sustainable energy facilities | I can bring all of my 30 students on a tour and not be split up | 8 | L | Not Started | 8
30 | Farmers market seller | unload my products onto 10ft loading dock | I will have enough space to unload and move my products without being in anyone else's way | 21 | L | Not Started | 10
32 | Farmers market seller | Have access to at least 2 6ft and/or 8ft tables | I do not have to bring my own tables to sell my products | 2 | L | Not Started | 10
40 | Farmers market seller | Come and set up my booth the night before for 3 hours | I am all ready to sell my products when the market opens | 13 | M | Not Started | 10
7 | Parent | Have clear lines of sight all the way across the Outdoor playground | I can always see my child/children to make sure they are safe | 5 | M | Not Started | 11
8 | Grandparent | Sit within 10 feet of the indoor/outdoor playgrounds | I can hear and watch my grandchild/children as they play | 5 | M | Not Started | 11
25 | Teenager | Apply to at least 2 different part time employment options at Titians Tower | I can make money while also attending school during the week | 3 | M | Not Started | 11
34 | Shop Owner | have easily accessible trash cans no less than 10ft away from my store front | Customers will discard their trash outside of my store | 13 | M | Not Started | 11
35 | Evironmentalist | go on a recycleables tour for less than $10 | I can actually watch my recycleables be turned into something useful again | 13 | M | Not Started | 12
36 | Teenager | buy a Bubble Tea for less than $5 | I can enjoy bubble tea while at Titans Tower | 21 | M | Not Started | 13
38 | Teenager | have access to a free place to chill and hangout with couches and chairs | I can read my comic books while hanging out at the mall | 34 | M | Not Started | 14
Fixes | Automatic doors not wired correctly into and out of the laser tag arenas.
Fixes | The Sets for the laser tag need to be adjusted to meet handicap accessibility standards.
Investigations | What are the ADA standards that we will have to meet within the Laser Tag Arenas?
Investigations | How should prices and bundles be set for the laser tag arenas so that it will be profitable and affordable ?
Investigations | what is the quality of laser tag equipment is the best for Titans Tower?
Investigations | Should we hire a game director to create the differing laser tag game styles?
Investigations | Where can be purchase affordable furnishings for the shopping center?
Investigations | How many social media posts should be posted during a typical day of operations
Technical | Terminals within the laser tag facility need to be debugged and further tested.
Technical | Live feed cameras are lagging from the laser tag arena to the observation deck
Technical | Phone and intercom systems need to be upgraded in order to imporve performance and acoustics.
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Fibonacci number....2,3,5,8,13,21,34,55
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: H, M, L
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Number of the Sprint